## Dashboard
ISLAMIC CORE BANKING SYSTEM — MODULE INVENTORY
Workflow-Driven Architecture · GCC-Grade · AAOIFI & IFRS Compliant
Prepared by Digibit Solutions Limited
Domain | Domain Name | Total Modules | Total Sub-Modules | Shariah Touchpoints | Workflow Complexity | Implementation Phase | Priority
D1 | Workflow & Platform Engine | 5 | 18 | 6 | Critical — Backbone | Phase 0 (Foundation) | P0
D2 | Core Banking Operations | 9 | 42 | 22 | Very High | Phase 1 (Go-Live) | P0
D3 | Treasury & Capital Markets | 4 | 16 | 8 | High | Phase 2 (Post Go-Live) | P1
D4 | Trade Finance | 3 | 14 | 6 | High | Phase 2 | P1
D5 | Digital & Channel Layer | 5 | 20 | 4 | Medium | Phase 1 (Go-Live) | P0
D6 | Risk, Compliance & Shariah Governance | 6 | 28 | 14 | Very High | Phase 1 (Go-Live) | P0
D7 | Analytics & Reporting | 3 | 12 | 4 | Medium | Phase 2 | P1
D8 | Administration & Integration | 4 | 16 | 3 | Medium | Phase 0 (Foundation) | P0
TOTAL | 8 Domains | 39 | 166 | 67

## Module Inventory
Module ID | Domain | Module Name | Sub-Module / Component | Description | Islamic Contract Type(s) | Shariah Touchpoint | Workflow Pattern | Maker-Checker Levels | SSB Review Required | GCC Regulator Relevance | AAOIFI FAS Reference | Data Residency Impact | Integration Dependencies | Implementation Phase | Complexity (H/M/L)
D1-01 | D1: Workflow & Platform | BPMN Workflow Engine | Process Designer | Visual BPMN 2.0 process modelling for all banking workflows | N/A | All workflows route through Shariah checkpoints | Orchestration | N/A | Yes — engine config | All GCC regulators | N/A | High — workflow state persisted locally | All modules | Phase 0 | H
D1-01 | D1: Workflow & Platform | BPMN Workflow Engine | State Machine Runtime | Executes workflow instances, manages transitions, SLA timers | N/A | Enforces SSB hold states | Orchestration | N/A | No | All | N/A | High | All modules | Phase 0 | H
D1-01 | D1: Workflow & Platform | BPMN Workflow Engine | SLA & Escalation Manager | Configurable SLA thresholds per workflow step with auto-escalation | N/A | SSB review SLA tracking | Timer-based | N/A | No | All | N/A | Medium | Notification Engine | Phase 0 | M
D1-02 | D1: Workflow & Platform | Business Rules Engine | Rule Repository | Centralised store for Shariah product rules, regulatory rules, pricing rules | All Islamic contracts | Product-level Shariah rules defined here | Configuration | N/A | Yes — rule changes | All | FAS 1, FAS 4 | High | Product Factory, Financing | Phase 0 | H
D1-02 | D1: Workflow & Platform | Business Rules Engine | Decision Tables | Tabular rule definitions for profit rates, eligibility, limits | All | Shariah-compliant rate structures | Lookup | N/A | Yes | All | FAS 6 | Medium | Financing, Deposits | Phase 0 | M
D1-02 | D1: Workflow & Platform | Business Rules Engine | Rule Versioning & Audit | Full version history of every rule change with approval trail | N/A | Shariah audit trail for rule changes | Approval | 2-level | Yes | All | N/A | High | Shariah Compliance Module | Phase 0 | M
D1-03 | D1: Workflow & Platform | Notification & Escalation Engine | Multi-Channel Dispatcher | SMS, email, push notification, in-app alerts — Arabic/English | N/A | Shariah approval notifications to SSB members | Event-driven | N/A | No | All | N/A | Medium | All modules | Phase 0 | M
D1-03 | D1: Workflow & Platform | Notification & Escalation Engine | Template Manager | Bilingual notification templates (Arabic primary, English secondary) | N/A | Shariah-compliant terminology enforcement | Configuration | N/A | Yes — template content | All | N/A | Low | CIF | Phase 0 | L
D1-04 | D1: Workflow & Platform | Maker-Checker-Approver Framework | Approval Chain Config | Configurable N-level approval chains per transaction type and amount threshold | N/A | SSB inserted as mandatory approver for defined triggers | Sequential / Parallel | 2–5 levels | Yes — SSB as approver | All | N/A | High | All transactional modules | Phase 0 | H
D1-04 | D1: Workflow & Platform | Maker-Checker-Approver Framework | Delegation & Substitution | Temporary delegation of approval authority during absence | N/A | SSB delegation rules (minimum quorum) | Delegation | N/A | Yes | All | N/A | Medium | User Management | Phase 0 | M
D1-05 | D1: Workflow & Platform | SSB Review Gateway | Fatwa Clearance Workflow | Dedicated workflow for new product/transaction Fatwa requests to SSB | All new products | Primary Shariah governance checkpoint | Review & Approve | SSB quorum | Yes — core function | All — SSB mandated in all GCC | FAS 1 | High — Fatwa records | Product Factory, Financing, Treasury | Phase 0 | H
D1-05 | D1: Workflow & Platform | SSB Review Gateway | Post-Trade Shariah Audit Queue | Automated flagging of transactions for retrospective SSB review | All | Retrospective compliance verification | Sampling + Exception | SSB | Yes | All | FAS 1, GSS | High | All transactional modules | Phase 0 | H
D1-05 | D1: Workflow & Platform | SSB Review Gateway | SSB Dashboard & Reporting | Dedicated SSB member interface — pending reviews, Fatwa registry, compliance stats | All | SSB operational interface | Dashboard | N/A | Yes | All | N/A | Medium | Analytics | Phase 0 | M
D2-01 | D2: Core Banking Ops | General Ledger | Multi-Currency GL Engine | Real-time GL posting with multi-currency, multi-entity support | N/A | Profit/loss posting must follow Islamic accounting standards | Auto-post on transaction | 2-level for manual JVs | No | All | FAS 1, FAS 2 | High — GL is sovereign data | All modules post to GL | Phase 1 | H
D2-01 | D2: Core Banking Ops | General Ledger | AAOIFI Chart of Accounts | Pre-configured CoA aligned to AAOIFI FAS with IFRS mapping | N/A | Islamic-specific account categories (Murabaha receivables, Ijarah assets, etc.) | Configuration | N/A | Yes — CoA structure | All | FAS 1–32 | High | Reporting | Phase 1 | H
D2-01 | D2: Core Banking Ops | General Ledger | Profit Equalisation Reserve (PER) / Investment Risk Reserve (IRR) | Automated reserve computation and GL posting per AAOIFI | Mudarabah | Mandatory Shariah governance — smoothing mechanism | Periodic batch | 3-level | Yes | All | FAS 6, FAS 11 | High | Profit Distribution, Deposits | Phase 1 | H
D2-01 | D2: Core Banking Ops | General Ledger | Hijri Calendar Engine | Dual calendar support — Gregorian and Hijri for contract dates, Zakat periods | All | Hijri dates for Islamic contract milestones | System service | N/A | Yes — calendar rules | All — especially KSA | N/A | Low | All date-dependent modules | Phase 1 | M
D2-02 | D2: Core Banking Ops | Customer Information File (CIF) | KYC/eKYC Onboarding | Customer onboarding with national ID integration (Absher, UAE Pass, Bahrain eKey) | N/A | Shariah-compliant product eligibility flagging | Multi-step workflow | 2-level | No | All — varies by jurisdiction | N/A | Very High — PII data | Digital Channels, AML | Phase 1 | H
D2-02 | D2: Core Banking Ops | Customer Information File (CIF) | UBO Registry | Ultimate Beneficial Owner identification and tracking (FATF compliant) | N/A | UBO screening for Shariah-restricted entities | Periodic review workflow | 2-level | No | All | N/A | High | AML/CFT, Risk | Phase 1 | M
D2-02 | D2: Core Banking Ops | Customer Information File (CIF) | Corporate & SME Onboarding | Complex entity onboarding — group structures, authorised signatories, trade licences | N/A | Entity-level Shariah product eligibility | Multi-step + document workflow | 3-level | No | All | N/A | Very High | Trade Finance, Financing | Phase 1 | H
D2-02 | D2: Core Banking Ops | Customer Information File (CIF) | Customer 360 View | Unified customer profile — accounts, financing, transactions, risk score, Shariah compliance status | N/A | Shariah compliance status per customer | Real-time aggregation | N/A | No | All | N/A | High | All modules | Phase 1 | M
D2-03 | D2: Core Banking Ops | Deposits — Wadiah (Current Accounts) | Wadiah Yad Dhamanah Accounts | Current accounts based on safekeeping with guarantee — no profit entitlement | Wadiah | No profit distribution — Hibah (gift) at bank's discretion only | Account opening workflow | 2-level | Yes — Hibah policy | All | FAS 2 | High | GL, CIF, Channels | Phase 1 | H
D2-03 | D2: Core Banking Ops | Deposits — Wadiah (Current Accounts) | Qard Hasan Accounts | Benevolent loan-based current accounts — depositor is lender to bank | Qard | No return permitted — any benefit voids the Qard | Account opening workflow | 2-level | Yes | Varies — KSA, Kuwait prefer Qard model | FAS 1 | High | GL, CIF | Phase 1 | M
D2-04 | D2: Core Banking Ops | Deposits — Mudarabah (Savings/Investment) | Mudarabah Savings Accounts | Profit-sharing savings — bank as Mudarib, depositor as Rab al-Mal | Mudarabah | Profit ratio must be agreed upfront, loss borne by depositor (capital) | Account opening + profit cycle | 2-level | Yes — profit ratios | All | FAS 3, FAS 6 | High | Profit Distribution, GL | Phase 1 | H
D2-04 | D2: Core Banking Ops | Deposits — Mudarabah (Savings/Investment) | Mudarabah Term Deposits | Fixed-term investment deposits with defined Mudarabah pools | Mudarabah | Pool segregation, profit allocation methodology must be SSB-approved | Account opening + maturity workflow | 2-level | Yes | All | FAS 3, FAS 6 | High | Profit Distribution, GL, Treasury | Phase 1 | H
D2-04 | D2: Core Banking Ops | Deposits — Mudarabah (Savings/Investment) | Wakala Bil Istithmar Deposits | Agency-based investment deposits — bank as agent invests on behalf of depositor | Wakalah | Expected profit rate is indicative only, not guaranteed | Account opening + periodic review | 2-level | Yes | UAE, Bahrain prefer Wakalah model | FAS 22 | High | GL, Treasury | Phase 1 | H
D2-05 | D2: Core Banking Ops | Financing — Murabaha | Commodity Murabaha (Tawarruq) | Cost-plus-profit sale of commodity — dominant GCC personal/corporate financing | Murabaha / Tawarruq | Commodity must be real, sequence must not be pre-arranged (debated) | Full lifecycle: request → credit check → commodity purchase → sale → repayment | 3-level + SSB for new structures | Yes | All — primary product in GCC | FAS 2, FAS 28 | High | GL, CIF, Payment Hub, Credit Risk | Phase 1 | H
D2-05 | D2: Core Banking Ops | Financing — Murabaha | Asset Murabaha | Direct cost-plus sale of identified asset (vehicle, equipment, property) | Murabaha | Bank must own asset before selling — constructive/physical possession | Lifecycle: request → valuation → purchase → markup → sale → delivery → repayment | 3-level | Yes | All | FAS 2, FAS 28 | High | GL, CIF, Collateral | Phase 1 | H
D2-06 | D2: Core Banking Ops | Financing — Ijarah | Ijarah (Operating Lease) | Islamic lease — bank retains ownership, lessee pays rental | Ijarah | Bank bears major maintenance (structural), lessee bears usufruct maintenance | Lifecycle: request → asset acquisition → lease contract → rental collection → return/renewal | 3-level | Yes | All | FAS 8, FAS 32 | High | GL, CIF, Fixed Assets | Phase 1 | H
D2-06 | D2: Core Banking Ops | Financing — Ijarah | Ijarah Muntahia Bittamleek (IMB) | Lease-to-own — ownership transfers at end via gift, sale, or gradual transfer | IMB | Transfer mechanism must be specified upfront, cannot be condition of lease | Full lifecycle + ownership transfer workflow | 3-level + SSB for transfer | Yes | All — dominant real estate financing | FAS 8, FAS 32 | High | GL, CIF, Collateral, Land Registry integration | Phase 1 | H
D2-07 | D2: Core Banking Ops | Financing — Musharakah | Diminishing Musharakah (Home Finance) | Joint ownership with gradual buyout — dominant GCC mortgage alternative | Diminishing Musharakah | Profit/loss shared per ownership ratio, buyout schedule pre-agreed | Lifecycle: request → valuation → joint purchase → rental + buyout schedule → full transfer | 3-level + SSB | Yes | All — primary home finance product | FAS 4 | High | GL, CIF, Collateral, Land Registry | Phase 1 | H
D2-07 | D2: Core Banking Ops | Financing — Musharakah | Full Musharakah (Project Finance) | Full partnership — bank and client as partners sharing profit and loss | Musharakah | Profit ratio can differ from capital ratio (by agreement), loss must follow capital ratio | Project lifecycle workflow with periodic P&L distribution | 3-level + SSB + Board | Yes | All | FAS 4 | High | GL, CIF, Risk | Phase 2 | H
D2-08 | D2: Core Banking Ops | Financing — Istisna'a & Salam | Istisna'a (Construction/Manufacturing) | Commissioned manufacturing — bank orders construction, sells to client | Istisna'a | Price fixed at inception, progressive billing permitted, parallel Istisna'a allowed | Lifecycle: contract → progress milestones → delivery → payment | 3-level | Yes | All | FAS 10 | Medium | GL, CIF, Collateral | Phase 2 | H
D2-08 | D2: Core Banking Ops | Financing — Istisna'a & Salam | Salam (Forward Sale) | Advance payment for future delivery of specified commodity | Salam | Full price paid upfront, commodity specs must be precise, no gold/silver/currency | Contract → payment → delivery → parallel Salam for hedging | 3-level | Yes | Limited use in GCC retail | FAS 7 | Medium | GL, Treasury | Phase 2 | M
D2-09 | D2: Core Banking Ops | Profit Distribution Engine | Pool Management | Creation and management of investment pools — general and restricted | Mudarabah / Wakalah | Pool segregation is fundamental Shariah requirement | Periodic batch (daily/monthly) | 3-level + SSB approval of methodology | Yes — methodology | All | FAS 6, FAS 11 | High | Deposits, GL, Treasury | Phase 1 | H
D2-09 | D2: Core Banking Ops | Profit Distribution Engine | Profit Calculation & Allocation | Weighted-average or tiered profit allocation per pool/product/customer | Mudarabah / Wakalah | Calculation methodology must be SSB-approved, transparent to depositors | Batch calculation + approval workflow | 3-level + SSB | Yes | All | FAS 6 | High | Deposits, GL | Phase 1 | H
D2-09 | D2: Core Banking Ops | Profit Distribution Engine | PER/IRR Management | Profit Equalisation Reserve and Investment Risk Reserve computation | Mudarabah | Smoothing mechanism — SSB must approve reserve policies | Periodic | 3-level + SSB | Yes | All | FAS 6, FAS 11 | High | GL | Phase 1 | H
D2-10 | D2: Core Banking Ops | Payment Hub | Domestic Payments (RTGS/ACH) | Integration with national payment systems — SARIE (KSA), UAEFTS, EFTS (Bahrain) | N/A | Payment screening for Shariah-restricted counterparties | Straight-through with exception workflow | 2-level for high-value | No | Jurisdiction-specific | N/A | High | GL, CIF, AML | Phase 1 | H
D2-10 | D2: Core Banking Ops | Payment Hub | Cross-Border (SWIFT) | SWIFT gpi integration for international transfers | N/A | Screening for Shariah non-compliant counterparties/activities | STP + sanctions screening | 2-level | No | All | N/A | High | GL, CIF, AML, Treasury | Phase 1 | H
D2-10 | D2: Core Banking Ops | Payment Hub | Instant Payments | Real-time payment integration — SARIE IPS (KSA), IPP (UAE), Fawri+ (Bahrain) | N/A | Same Shariah screening as domestic | Real-time | 1-level (auto) | No | Jurisdiction-specific | N/A | High | GL, CIF, Channels | Phase 1 | H
D2-11 | D2: Core Banking Ops | Fee & Charges Engine | Fee Configuration | Configurable fee schedules per product, customer segment, channel | N/A | Fees must not be Riba — cannot compound, must relate to actual service | Configuration + approval | 2-level + SSB for new fee types | Yes — new fee structures | All | N/A | Low | All transactional modules | Phase 1 | M
D2-11 | D2: Core Banking Ops | Fee & Charges Engine | Late Payment Handling | Charity-based late payment charges — proceeds to charity, not bank revenue | N/A | Critical Shariah point — late fees go to charity fund, not P&L | Auto-calculation + charity allocation workflow | 2-level + SSB policy | Yes — mandatory | All | FAS 28 | Low | Financing modules, GL | Phase 1 | H
D3-01 | D3: Treasury | Sukuk Management | Sukuk Portfolio Tracker | Position management for Sukuk holdings — Al-Ijarah, Al-Mudarabah, Al-Wakalah types | Various Sukuk structures | Each Sukuk structure has distinct Shariah requirements | Trade lifecycle workflow | 3-level + SSB for new structures | Yes | All | FAS 17, FAS 25 | High | GL, Risk | Phase 2 | H
D3-01 | D3: Treasury | Sukuk Management | Coupon/Profit Processing | Periodic Sukuk profit receipt processing and GL posting | Sukuk | Profit must derive from underlying asset performance | Batch + auto-posting | 2-level | No | All | FAS 17 | Medium | GL, Profit Distribution | Phase 2 | M
D3-02 | D3: Treasury | Interbank Placements | Commodity Murabaha Placements | Short-term interbank placements via commodity Murabaha | Murabaha | Commodity must be real and independently verified | Deal workflow: quote → execute → settle | 3-level | Yes — counterparty list | All | FAS 2 | High | GL, Liquidity, Risk | Phase 2 | H
D3-02 | D3: Treasury | Interbank Placements | Wakalah Placements | Agency-based interbank investments | Wakalah | Agent bank must invest in Shariah-compliant assets | Deal + monitoring workflow | 3-level | Yes | UAE, Bahrain | FAS 22 | High | GL, Risk | Phase 2 | H
D3-03 | D3: Treasury | Foreign Exchange | Spot FX | Immediate currency exchange at spot rate | Bay' al-Sarf | Must settle same day or T+2 max — deferred settlement of currency is Riba | Deal workflow: quote → confirm → settle | 2-level | No | All | FAS 1 | Medium | GL, Payment Hub | Phase 2 | M
D3-03 | D3: Treasury | Foreign Exchange | Islamic Hedging (Wa'ad) | Unilateral promise-based FX hedging — permitted alternative to conventional forwards | Wa'ad | Must be unilateral (not bilateral), cannot be binding on both parties simultaneously | Wa'ad issuance → exercise/expiry workflow | 3-level + SSB | Yes — each structure | Varies — SAMA, CBUAE allow | AAOIFI Shariah Standard 48 | High | GL, Risk | Phase 2 | H
D3-04 | D3: Treasury | Liquidity Management | Liquidity Position Monitor | Real-time liquidity dashboard across all currencies and entities | N/A | Islamic liquidity instruments only — no conventional repo | Real-time aggregation | N/A | No | All | N/A | High | GL, All treasury modules | Phase 2 | H
D3-04 | D3: Treasury | Liquidity Management | Collateralised Murabaha Repo | Islamic alternative to conventional repo — Murabaha-based collateral arrangement | Murabaha | Must involve genuine sale, not just collateral pledging | Deal lifecycle | 3-level + SSB | Yes | Varies | FAS 2 | High | GL, Sukuk | Phase 2 | H
D4-01 | D4: Trade Finance | Islamic Letters of Credit | Wakalah-Based LC | LC where bank acts as agent (Wakil) for importer — fee-based | Wakalah | Bank earns agency fee, not interest on financing | Full LC lifecycle: application → issuance → advising → documents → payment → settlement | 3-level | Yes | All | FAS 22, AAOIFI SS 5 | Medium | GL, CIF, Payment Hub, SWIFT | Phase 2 | H
D4-01 | D4: Trade Finance | Islamic Letters of Credit | Murabaha-Based LC | LC with embedded Murabaha financing — bank purchases goods, sells to importer at markup | Murabaha | Bank must take ownership/possession of goods before selling | LC lifecycle + Murabaha contract workflow | 3-level + SSB | Yes | All | FAS 2, FAS 28 | Medium | GL, CIF, Financing, Payment Hub | Phase 2 | H
D4-01 | D4: Trade Finance | Islamic Letters of Credit | Musharakah LC | LC with partnership structure — bank and importer share in trade transaction | Musharakah | Profit/loss sharing per agreed ratio | LC + Musharakah contract workflow | 3-level + SSB | Yes | Limited use | FAS 4 | Medium | GL, CIF, Payment Hub | Phase 2 | H
D4-02 | D4: Trade Finance | Islamic Guarantees (Kafalah) | Financial Guarantee | Bank guarantees payment obligation of client — Kafalah structure | Kafalah | Guarantee fee must not relate to guaranteed amount over time (avoiding Riba) | Guarantee lifecycle: application → issuance → claim/expiry | 3-level | Yes — fee structure | All | AAOIFI SS 5 | Medium | GL, CIF, Credit Risk | Phase 2 | H
D4-02 | D4: Trade Finance | Islamic Guarantees (Kafalah) | Performance Guarantee | Bank guarantees performance/delivery by client | Kafalah | Same Shariah considerations — fee not time-value based | Guarantee lifecycle | 3-level | Yes | All | AAOIFI SS 5 | Medium | GL, CIF | Phase 2 | M
D4-02 | D4: Trade Finance | Islamic Guarantees (Kafalah) | Bid Bond | Guarantee for tender/bid processes | Kafalah | Fee structure must be Shariah-compliant | Issuance → claim/release | 2-level | No | All | AAOIFI SS 5 | Low | GL, CIF | Phase 2 | L
D4-03 | D4: Trade Finance | Documentary Collections | Import Collection | Document handling for import transactions — D/P and D/A terms | N/A (service-based) | Service fee only — no interest on deferred payment handling | Document lifecycle workflow | 2-level | No | All | N/A | Low | GL, CIF, SWIFT | Phase 2 | M
D4-03 | D4: Trade Finance | Documentary Collections | Export Collection | Document handling for export transactions | N/A (service-based) | Service fee only | Document lifecycle | 2-level | No | All | N/A | Low | GL, CIF, SWIFT | Phase 2 | M
D5-01 | D5: Digital Channels | Internet Banking | Retail Internet Banking | Full-service web portal — account view, transfers, financing applications, profit statements | N/A (channel) | Islamic product terminology, Shariah-compliant product display | Self-service + workflow initiation | Biometric/OTP | No | All | N/A | High — session data, PII | CIF, All products, Payment Hub | Phase 1 | H
D5-01 | D5: Digital Channels | Internet Banking | Corporate Internet Banking | Multi-user corporate portal with role-based access, bulk payments, trade finance initiation | N/A (channel) | Islamic corporate product workflows | Multi-signer approval workflows | Multi-signer | No | All | N/A | High | CIF, Payments, Trade Finance | Phase 1 | H
D5-02 | D5: Digital Channels | Mobile Banking | Retail Mobile App | Native iOS/Android app with biometric auth, national ID login (Absher/UAE Pass) | N/A (channel) | Arabic-first UI, Islamic terminology, prayer time integration | Self-service + workflow | Biometric | No | All | N/A | Very High — mobile data | CIF, All products, Payments | Phase 1 | H
D5-02 | D5: Digital Channels | Mobile Banking | QR Payments & Wallet | QR code-based merchant payments and digital wallet | N/A (channel) | Merchant screening for Shariah-compliant businesses | Instant | Biometric | No | KSA (mada Pay), UAE (JAYWAN) | N/A | High | Payment Hub, CIF | Phase 1 | M
D5-03 | D5: Digital Channels | Agent Banking | Agent Onboarding & Management | Agent network management — onboarding, limits, commissions, reconciliation | Wakalah (agency) | Agent acts as Wakil — agency fee structure must be Shariah-compliant | Onboarding workflow + daily reconciliation | 2-level | Yes — agency structure | Varies — more relevant in Oman, Bahrain | FAS 22 | Medium | CIF, Payments, GL | Phase 2 | M
D5-04 | D5: Digital Channels | Card Management | Debit Card Issuance & Management | Card lifecycle — issuance, activation, blocking, replacement, limits | N/A | Card usage restricted to Shariah-compliant merchants (optional strict mode) | Card lifecycle workflow | 2-level | No | All | N/A | High — PCI DSS | CIF, Deposits, Payment Hub | Phase 1 | H
D5-04 | D5: Digital Channels | Card Management | Prepaid Card / Shariah-Compliant Credit Card | Prepaid or charge card (Ujrah/Tawarruq-based credit card) | Tawarruq / Ujrah | No conventional revolving credit — must be structured Islamically | Card lifecycle + financing workflow (if credit) | 3-level + SSB for credit card | Yes — credit card structure | All — active debate on structures | FAS 2, FAS 28 | High — PCI DSS | CIF, Financing, Payment Hub | Phase 2 | H
D5-05 | D5: Digital Channels | Open Banking / API Gateway | API Management Platform | Developer portal, API key management, rate limiting, versioning | N/A | Third-party access must not expose non-Shariah product data | API lifecycle | 2-level | No | KSA (SAMA Open Banking), UAE (AANI), Bahrain (BH Open Banking) | N/A | Very High — data sharing | All modules exposing APIs | Phase 1 | H
D5-05 | D5: Digital Channels | Open Banking / API Gateway | Consent Management | Customer consent framework for third-party data access (PSD2-equivalent) | N/A | Consent scope must respect Islamic product confidentiality | Consent workflow — grant/revoke/expire | Customer-initiated | No | KSA, UAE, Bahrain mandated | N/A | Very High | CIF, All products | Phase 1 | H
D6-01 | D6: Risk & Compliance | Shariah Compliance Engine | Product Fatwa Registry | Centralised registry of all Fatwa issued by SSB — linked to products | All | Core Shariah governance artifact | Fatwa lifecycle: request → review → issuance → annual renewal | SSB | Yes — core | All — SSB mandated | AAOIFI GSS | High | Product Factory, All products | Phase 1 | H
D6-01 | D6: Risk & Compliance | Shariah Compliance Engine | Transaction Shariah Screening | Real-time screening of transactions against Shariah rules (e.g. Haram merchant categories) | All | Prevents non-compliant transactions before posting | Real-time + exception workflow | Auto + 2-level escalation | No (rule-based) | All | AAOIFI GSS | Medium | All transactional modules | Phase 1 | H
D6-01 | D6: Risk & Compliance | Shariah Compliance Engine | Shariah Audit Module | Internal Shariah audit — sampling, findings, corrective actions, SSB reporting | All | Annual Shariah audit mandated in all GCC jurisdictions | Audit lifecycle workflow | Shariah auditor → SSB | Yes | All | AAOIFI GSAS, ASIFI | High | All modules | Phase 1 | H
D6-01 | D6: Risk & Compliance | Shariah Compliance Engine | Shariah Non-Compliance Income (SNCI) Purification | Identification and quarantine of income earned from non-compliant sources | All | Mandatory purification — SNCI donated to charity | Detection → quarantine → charity distribution workflow | 3-level + SSB | Yes | All | AAOIFI GSS | High | GL, All revenue-generating modules | Phase 1 | H
D6-02 | D6: Risk & Compliance | AML/CFT & Sanctions | Transaction Monitoring | Real-time and batch monitoring against AML typologies and suspicious patterns | N/A | Islamic-specific typologies (e.g. Tawarruq layering) | Detection → alert → investigation → SAR workflow | 3-level + MLRO | No | All — FATF + local FIU | N/A | Very High | All transactional modules, CIF | Phase 1 | H
D6-02 | D6: Risk & Compliance | AML/CFT & Sanctions | Sanctions Screening | Real-time screening against OFAC, EU, UN, local lists (CBUAE GoAML, SAMA lists) | N/A | N/A (regulatory, not Shariah) | Real-time + exception | Auto + 2-level | No | All | N/A | Very High | CIF, Payments, Trade Finance | Phase 1 | H
D6-02 | D6: Risk & Compliance | AML/CFT & Sanctions | STR/SAR Filing | Suspicious Transaction/Activity Report generation and submission to FIU | N/A | N/A | Investigation → approval → submission workflow | 3-level + MLRO + compliance officer | No | All — jurisdiction-specific FIU | N/A | Very High | CIF, Transaction Monitoring | Phase 1 | H
D6-03 | D6: Risk & Compliance | Credit Risk Management | Islamic Credit Scoring | Credit scoring adapted for Islamic financing — NPF instead of NPL metrics | All financing | Risk assessment must account for Islamic contract-specific risks | Scoring workflow: application → auto-score → override → approval | 3-level | No | All | N/A | High | Financing modules, CIF | Phase 1 | H
D6-03 | D6: Risk & Compliance | Credit Risk Management | IFRS 9 ECL (Islamic Adaptation) | Expected Credit Loss computation adapted for Islamic financing portfolios | All financing | PD/LGD/EAD models must account for Murabaha/Ijarah/Musharakah-specific cashflow patterns | Batch calculation + review workflow | 3-level | No | All | FAS 30 (AAOIFI equivalent) | High | Financing, GL, Reporting | Phase 1 | H
D6-03 | D6: Risk & Compliance | Credit Risk Management | Collateral Management | Collateral registration, valuation, revaluation, release workflow | All secured financing | Islamic collateral rules — Rahn (pledge) specific requirements | Collateral lifecycle workflow | 2-level | No | All | AAOIFI SS 39 | High | Financing modules, GL | Phase 1 | H
D6-04 | D6: Risk & Compliance | Operational Risk | Incident & Loss Event Management | Capture, classify, escalate operational risk events (Basel III) | N/A | Shariah non-compliance events tracked as operational risk sub-category | Incident workflow: capture → classify → escalate → remediate → close | 3-level | No | All | N/A | Medium | All modules | Phase 2 | M
D6-04 | D6: Risk & Compliance | Operational Risk | Key Risk Indicators (KRIs) | Dashboard of leading risk indicators with threshold-based alerting | N/A | Islamic-specific KRIs: Shariah breach rate, SNCI ratio, SSB rejection rate | Periodic calculation + alert | N/A | No | All | N/A | Medium | All modules, Analytics | Phase 2 | M
D6-05 | D6: Risk & Compliance | Regulatory Reporting | SAMA Prudential Returns (KSA) | Automated generation of SAMA regulatory returns — capital adequacy, large exposures, liquidity | All | Islamic-specific ratios and breakdowns per SAMA requirements | Generation → review → approval → submission workflow | 3-level + CFO/CRO | No | KSA (SAMA) | SAMA Prudential Framework | Very High | GL, All modules | Phase 1 | H
D6-05 | D6: Risk & Compliance | Regulatory Reporting | CBUAE EPRS (UAE) | CBUAE Electronic Prudential Reporting System submission | All | Islamic-specific schedules | Same as above | 3-level | No | UAE (CBUAE) | CBUAE Regulations | Very High | GL, All modules | Phase 1 | H
D6-05 | D6: Risk & Compliance | Regulatory Reporting | Multi-Jurisdiction Template Engine | Configurable template engine supporting CBB, QCB, CBO, CBK return formats | All | Each jurisdiction has Islamic-specific schedules | Template config + generation workflow | 3-level | No | Bahrain, Qatar, Oman, Kuwait | Various | Very High | GL, All modules | Phase 1 | H
D6-06 | D6: Risk & Compliance | Zakat Computation | Zakat Base Calculation | Annual Zakat computation per AAOIFI — net assets method or net invested funds method | N/A | Zakat is a Shariah pillar — computation methodology must be SSB-approved | Annual batch → review → SSB approval → disbursement | 3-level + SSB | Yes | All — KSA mandatory (ZATCA), others voluntary | FAS 9 | High | GL, All asset modules | Phase 1 | H
D6-06 | D6: Risk & Compliance | Zakat Computation | ZATCA Integration (KSA) | Direct integration with Saudi Zakat, Tax & Customs Authority for Zakat filing | N/A | ZATCA compliance is regulatory mandate in KSA | Filing workflow | 3-level | No | KSA (ZATCA) | ZATCA Regulations | Very High | Zakat Base, GL | Phase 1 (KSA) | H
D7-01 | D7: Analytics | Management Information System (MIS) | Executive Dashboard | Real-time KPI dashboard — profitability, NPF ratio, liquidity, Shariah compliance score | N/A | Islamic-specific KPIs: SNCI rate, Shariah breach count, Zakat accuracy | Real-time aggregation | N/A | No | All | N/A | Medium | All modules | Phase 2 | M
D7-01 | D7: Analytics | Management Information System (MIS) | Branch/Channel Performance | Performance analytics by branch, channel, product, segment | N/A | Islamic product performance segmentation | Batch + real-time | N/A | No | All | N/A | Medium | All modules | Phase 2 | M
D7-02 | D7: Analytics | AAOIFI Financial Statements | Statement of Financial Position | Balance sheet per AAOIFI FAS presentation requirements | All | Islamic-specific line items (Murabaha receivables, Ijarah assets, Mudarabah pools) | Period-end generation workflow | 3-level + external audit | Yes — SSB sign-off | All | FAS 1 | High | GL | Phase 2 | H
D7-02 | D7: Analytics | AAOIFI Financial Statements | Income Statement (AAOIFI) | Income statement with Islamic-specific revenue recognition | All | Revenue recognition differs by contract type — must follow FAS | Period-end generation | 3-level + audit | Yes | All | FAS 1, contract-specific FAS | High | GL | Phase 2 | H
D7-02 | D7: Analytics | AAOIFI Financial Statements | Statement of Sources & Uses of Zakah | Zakat fund statement per AAOIFI FAS 9 | N/A | Mandatory AAOIFI financial statement for Islamic banks | Annual generation | 3-level + SSB | Yes | All | FAS 9 | Medium | Zakat module, GL | Phase 2 | M
D7-02 | D7: Analytics | AAOIFI Financial Statements | Statement of Restricted Investments | Reporting on restricted Mudarabah/Wakalah investment pools | Mudarabah / Wakalah | Segregated reporting per pool — depositor transparency requirement | Period-end generation | 3-level | Yes | All | FAS 6 | High | Deposits, Profit Distribution, GL | Phase 2 | H
D7-03 | D7: Analytics | Data Warehouse & BI | ETL Pipeline | Extract-Transform-Load from CBS to analytical data warehouse | N/A | Islamic contract attributes must be preserved in warehouse schema | Scheduled batch | N/A | No | All | N/A | High — data residency | All modules | Phase 2 | H
D7-03 | D7: Analytics | Data Warehouse & BI | Self-Service BI Portal | Business user analytical tools — ad hoc queries, report builder, visualisation | N/A | Pre-built Islamic banking analytical models | Self-service | N/A | No | All | N/A | High | Data Warehouse | Phase 2 | M
D8-01 | D8: Administration | User & Role Management | RBAC Engine | Role-based access control with Islamic banking role templates | N/A | SSB member roles with elevated access to Shariah artifacts | User lifecycle workflow | 2-level | No | All | N/A | Very High | All modules | Phase 0 | H
D8-01 | D8: Administration | User & Role Management | National SSO Integration | Integration with national identity providers — Absher (KSA), UAE Pass, Bahrain eKey | N/A | N/A (authentication) | SSO federation | N/A | No | Jurisdiction-specific | N/A | Very High | CIF, Digital Channels | Phase 0 | H
D8-02 | D8: Administration | Product Factory | No-Code Product Configuration | Visual product builder — define Islamic contract parameters, pricing, eligibility, workflow | All | Every product must map to an approved Shariah contract with SSB Fatwa | Product lifecycle: design → SSB review → pilot → launch → retire | 3-level + SSB mandatory | Yes — mandatory for every product | All | All contract-specific FAS | Medium | Rules Engine, Workflow Engine, All product modules | Phase 0 | H
D8-02 | D8: Administration | Product Factory | Product Catalogue & Versioning | Catalogue of all live, pilot, and retired products with version history | All | Shariah compliance status per product version | Version control workflow | 2-level | Yes | All | N/A | Medium | All product modules | Phase 0 | M
D8-03 | D8: Administration | Integration Bus / ESB | API Gateway & Service Mesh | Enterprise integration layer — REST/SOAP/messaging for all internal and external integrations | N/A | N/A (infrastructure) | Event-driven + synchronous | N/A | No | All | N/A | High | All modules, external systems | Phase 0 | H
D8-03 | D8: Administration | Integration Bus / ESB | Third-Party Connectors | Pre-built connectors: credit bureaus (SIMAH-KSA, Al Etihad-UAE), SWIFT, national switches | N/A | Credit bureau data used within Shariah-compliant decisioning | Connector lifecycle | 2-level | No | Jurisdiction-specific | N/A | High | CIF, Payments, Risk, Trade Finance | Phase 0 | H
D8-04 | D8: Administration | Document Management | Document Repository | Centralised document store — contracts, Fatwa, regulatory correspondence, customer documents | N/A | Fatwa documents and Shariah audit reports stored with controlled access | Document lifecycle + retention policy | 2-level | No | All | N/A | High — regulatory retention | All modules | Phase 0 | M
D8-04 | D8: Administration | Document Management | e-Signature Integration | Digital signature integration — government-backed (Absher, UAE Pass) and commercial (DocuSign) | N/A | Islamic contract signing — must meet Shariah requirements for valid Aqd (contract) | Signing workflow | Multi-party | Yes — for financing contracts | All — digital-first mandates | N/A | Very High | Financing, Trade Finance, CIF | Phase 0 | H

## Shariah Touchpoints
Touchpoint ID | Module | Sub-Module | Touchpoint Description | Shariah Risk Level (H/M/L) | SSB Involvement | Governing AAOIFI Standard | Workflow Checkpoint Type | Frequency | Remediation if Breached
ST-001 | Product Factory | Product Configuration | Every new product must have an SSB-issued Fatwa before launch | H | Mandatory — SSB quorum approval | AAOIFI GSS | Pre-launch gate | Per new product / material change | Product launch blocked until Fatwa obtained
ST-002 | Financing — Murabaha | Commodity Murabaha | Bank must take ownership/possession of commodity before selling to client | H | SSB audit sampling | FAS 2, FAS 28, SS 8 | Transaction-level | Every transaction | Transaction voided, income purified to charity
ST-003 | Financing — Murabaha | Asset Murabaha | Asset must be in bank's constructive possession before sale to client | H | SSB audit sampling | FAS 2, SS 8 | Transaction-level | Every transaction | Transaction voided, income purified
ST-004 | Financing — Ijarah | IMB | Ownership transfer mechanism must be separate from lease contract | H | SSB review of contract structure | FAS 8, FAS 32, SS 9 | Contract-level | Every contract | Contract restructured or voided
ST-005 | Financing — Musharakah | Diminishing Musharakah | Loss must be borne proportional to capital contribution (not profit ratio) | H | SSB policy approval | FAS 4, SS 12 | Contract-level | Every loss event | Loss reallocation + SSB review
ST-006 | Deposits — Mudarabah | Profit Distribution | Profit-sharing ratio must be agreed at inception, not as a fixed amount | H | SSB methodology approval | FAS 3, FAS 6, SS 13 | Account opening + distribution | Every account + every distribution cycle | Distribution recalculated, excess returned
ST-007 | Profit Distribution Engine | Pool Management | Investment pools must be genuinely segregated — no commingling of restricted/unrestricted | H | SSB annual audit | FAS 6, FAS 11 | Operational | Continuous | Pool remediation + SNCI purification
ST-008 | Profit Distribution Engine | PER/IRR | PER/IRR reserves must have SSB-approved policy — not used to guarantee returns | H | SSB policy approval + annual review | FAS 6, FAS 11 | Policy-level | Annual review | Reserve policy amended + SSB reapproval
ST-009 | Fee & Charges Engine | Late Payment | Late payment charges must be donated to charity — cannot be bank revenue | H | SSB mandatory policy | FAS 28, SS 3 | Transaction-level | Every late payment | Income reversed from P&L to charity fund
ST-010 | Treasury — FX | Islamic Hedging | Wa'ad must be unilateral — bilateral binding promise constitutes forbidden derivative | H | SSB approval per structure | AAOIFI SS 48 | Deal-level | Every Wa'ad | Deal unwound, income purified
ST-011 | Treasury — Sukuk | Sukuk Portfolio | Underlying asset must be real and identifiable — not a debt obligation | H | SSB approval for each Sukuk investment | FAS 17, FAS 25, SS 17 | Investment-level | Every new Sukuk position | Position liquidated
ST-012 | Trade Finance — LC | Murabaha LC | Bank must take constructive possession of goods in LC transaction | H | SSB audit sampling | FAS 2, SS 8 | Transaction-level | Every Murabaha LC | Transaction restructured or voided
ST-013 | Card Management | Credit Card | Credit card structure (Tawarruq/Ujrah) must have dedicated SSB Fatwa | H | SSB Fatwa required | FAS 2, FAS 28 | Product-level | Product launch + annual review | Product suspended until compliant
ST-014 | Shariah Compliance Engine | SNCI Purification | All non-compliant income must be identified, quarantined, and donated to charity | H | SSB oversight + annual certification | AAOIFI GSS | Continuous + periodic | Continuous monitoring + annual review | SNCI purified immediately upon detection
ST-015 | Shariah Compliance Engine | Transaction Screening | Transactions with Haram merchants/counterparties must be blocked or flagged | M | Rule-based (SSB defines rules) | AAOIFI GSS | Real-time | Every transaction | Transaction blocked or escalated
ST-016 | Zakat Computation | Zakat Calculation | Zakat base and computation methodology must be SSB-approved | H | SSB approval + certification | FAS 9 | Annual | Annual | Zakat recalculated with corrected methodology
ST-017 | General Ledger | Chart of Accounts | CoA must separate Islamic product categories per AAOIFI | M | SSB review of CoA structure | FAS 1 | Configuration | At setup + material changes | CoA restructured
ST-018 | Deposits — Wadiah | Current Accounts | No profit distribution on Wadiah — only Hibah at bank's discretion | M | SSB Hibah policy | FAS 2 | Policy-level | Per Hibah decision | Hibah reversed if found systematic
ST-019 | Open Banking / API | Consent Management | Third-party access must not expose customer's Islamic financing details inappropriately | M | SSB data privacy policy | N/A | Configuration | Per consent grant | Access revoked
ST-020 | Shariah Compliance Engine | Shariah Audit | Annual internal Shariah audit is mandatory in all GCC jurisdictions | H | SSB receives and certifies audit results | AAOIFI GSAS, ASIFI | Annual cycle | Annual | Regulatory sanction + remediation plan
ST-021 | Document Management | e-Signature | Islamic financing contracts must meet requirements of valid Aqd (offer + acceptance) | M | SSB contract template approval | Shariah principles of Aqd | Contract-level | Every financing contract | Contract re-executed
ST-022 | Financing — Salam | Forward Sale | Full payment must be made at contract inception — deferred payment voids the Salam | H | SSB contract review | FAS 7, SS 7 | Contract-level | Every Salam contract | Contract voided

## GCC Regulatory Map
Module / Area | SAMA (KSA) | CBUAE (UAE) | CBB (Bahrain) | QCB (Qatar) | CBK (Kuwait) | CBO (Oman) | Key Requirement Notes
SSB Governance | Mandatory — SAMA SSB Framework | Mandatory — Higher Sharia Authority + bank SSB | Mandatory — CBB Sharia Governance Module | Mandatory — QCB Sharia Supervision | Mandatory — CBK Islamic Banking Dept. | Mandatory — CBO Islamic Banking Framework | All GCC mandate SSB; UAE has centralised Higher Sharia Authority since 2018
Shariah Audit | Annual — SAMA circular | Annual — CBUAE regulation | Annual — CBB rulebook HC-6 | Annual — QCB requirement | Annual — CBK requirement | Annual — CBO requirement | Internal + external Shariah audit mandated across all six
Capital Adequacy | SAMA Basel III + Islamic window | CBUAE Capital Standards | CBB Capital Adequacy (HC-1) | QCB Capital Framework | CBK Capital Requirements | CBO Capital Framework | All follow Basel III adapted for Islamic finance; IFSB guidance applied
Liquidity (LCR/NSFR) | SAMA Liquidity Coverage | CBUAE LCR/NSFR framework | CBB LM Module | QCB Liquidity Framework | CBK Liquidity Requirements | CBO Liquidity Standards | Sukuk and Islamic instruments eligible as HQLA with haircuts
AML/CFT | SAMA + SAFIU | CBUAE + goAML | CBB + FIU Bahrain | NAMLC Qatar | CBK + Kuwait FIU | CBO + ROP FIU | All aligned to FATF; jurisdiction-specific STR/SAR channels
Open Banking | SAMA Open Banking Framework (launched) | CBUAE AANI + Open Finance | CBB Open Banking Regulation | QCB — in development | CBK — early stage | CBO — not yet mandated | KSA and UAE most advanced; Bahrain operational since 2020
Data Residency | PDPL (Saudi Personal Data Protection Law) | DIFC/ADGM Data Protection + Federal DP Law | PDPL Bahrain | Qatar Data Privacy Law | Kuwait — sector guidance | Oman Data Protection Law | KSA PDPL most restrictive — data must reside in-kingdom for sovereign sectors
Zakat | Mandatory — ZATCA (Authority for Zakat, Tax) | Voluntary — bank-level | Voluntary — bank-level | Voluntary | Voluntary | Voluntary | Only KSA mandates institutional Zakat via ZATCA; others compute per AAOIFI FAS 9
VAT | 5% standard rate | 5% standard rate | 10% (increased 2022) | No VAT (as of 2025) | No VAT (as of 2025) | 5% standard rate | Bank fee structures must account for VAT on services
Payment Systems | SARIE (RTGS) + SARIE IPS (Instant) + mada | UAEFTS + IPP + JAYWAN | EFTS + Fawri+ (Instant) | QPAY + QMR | KASSIP + KNET | CBO RTGS + mPay | CBS must integrate with national payment infrastructure
Regulatory Reporting | SAMA Prudential Returns (XBRL migration underway) | CBUAE EPRS | CBB Online Returns | QCB Statistical Returns | CBK Reporting Framework | CBO Returns Portal | Each jurisdiction has proprietary return formats; some moving to XBRL
National ID Integration | Absher + Nafath (digital identity) | UAE Pass (unified ID) | Bahrain eKey | Qatar ID | Kuwait PACI | Oman Digital Identity | Critical for eKYC and digital onboarding
Credit Bureau | SIMAH | Al Etihad Credit Bureau (AECB) | CREDIMAX / BENEFIT | Qatar Credit Bureau | Ci-Net | Oman Credit Bureau (Mala'a) | CBS must integrate for credit decisioning
Profit Rate Benchmark | SAIBOR (phasing to new benchmark) | EIBOR | BIBOR | QCB Deposit Rate | CBK Discount Rate | CBO Repo Rate | Islamic banks use these as indicative benchmarks for pricing — not as interest

## Implementation Phases
Phase | Phase Name | Duration (months) | Key Modules | Key Deliverables | Go/No-Go Criteria | Dependencies
Phase 0 | Foundation & Platform | 4–6 | Workflow Engine, Rules Engine, Maker-Checker Framework, SSB Gateway, User Management, Product Factory, Integration Bus, Document Management | Platform infrastructure, BPMN engine deployed, RBAC configured, SSB workflow operational, Product Factory live with first product templates, ESB/API gateway operational | Workflow engine processes test transactions end-to-end; SSB can review and approve test products; National ID SSO functional | Infrastructure provisioning, SSB appointment, Regulator engagement
Phase 1 | Core Banking Go-Live | 8–12 | GL, CIF, Wadiah Deposits, Mudarabah Deposits, Murabaha Financing, Ijarah Financing, Diminishing Musharakah, Payment Hub, Fee Engine, Profit Distribution Engine, Shariah Compliance Engine, AML/CFT, Credit Risk, Regulatory Reporting, Zakat (KSA), Internet Banking, Mobile Banking, Card Management (Debit), Open Banking API | Core banking live with full transaction processing, Shariah compliance engine operational, AML/CFT live with regulator connectivity, Digital channels (web + mobile) launched, First regulatory return submitted, Profit distribution cycle completed successfully | Full transaction lifecycle tested; SSB certification of all live products; Regulatory approval for launch; AML/CFT connectivity to FIU confirmed; Profit distribution dry run accepted by SSB; Penetration test passed | Phase 0 complete, Central bank licence conditions met, Core team trained
Phase 2 | Product Expansion & Advanced | 6–8 | Musharakah (Full), Istisna'a, Salam, Wakalah Deposits, Sukuk Management, Interbank Placements, FX & Hedging, Liquidity Management, Trade Finance (LC, Kafalah, Collections), Agent Banking, Prepaid/Credit Card, Operational Risk, Advanced Analytics, AAOIFI Financial Statements, Data Warehouse | Treasury operations live, Trade finance operational, Advanced product suite available, Full AAOIFI financial statement generation, BI/analytics platform live, Agent banking network (if applicable) | Treasury dealing room operational; Trade finance LC processed end-to-end; AAOIFI financial statements generated and audited; Credit card structure SSB-approved; Data warehouse populated with 6+ months of data | Phase 1 stable (3+ months), Treasury team onboarded, Trade finance team trained
Phase 3 | Optimisation & Scale | Ongoing | Performance tuning, AI/ML credit scoring, Advanced analytics, Cross-border expansion modules, Regulatory change management | Performance benchmarks met, ML models trained on live data, Regulatory change framework operational, Multi-entity/multi-jurisdiction support if needed | System handles 5x projected peak load; ML models outperform rule-based scoring; Regulator satisfied with ongoing returns quality | 12+ months of live data, Stable operations

## Integration Matrix
Source Module | Target Module | Integration Type | Data Exchanged | Frequency | Protocol | Shariah Relevance | Criticality (H/M/L)
All Transactional Modules | General Ledger | Event-driven | Journal entries, postings | Real-time | Internal API / Event bus | GL must separate Islamic accounting categories | H
CIF | AML/CFT | Event-driven | Customer data, KYC status, risk score | Real-time on onboarding + periodic | Internal API | Shariah-restricted entity screening | H
Financing Modules | Credit Risk | Request-Response | Financing application data, collateral, cashflows | Per application + periodic portfolio | Internal API | Islamic-specific PD/LGD models | H
Financing Modules | Profit Distribution Engine | Batch | Financing income, pool assignments | Daily / Monthly | Batch job | Profit must be from Shariah-compliant activity | H
Deposits | Profit Distribution Engine | Batch | Deposit balances, pool assignments, weightages | Daily / Monthly | Batch job | Distribution methodology SSB-approved | H
Payment Hub | AML/CFT | Real-time | Payment details for sanctions screening | Every payment | Internal API + MQ | Screening for Haram counterparties | H
Payment Hub | National Payment Systems | Real-time | Payment instructions (SARIE, UAEFTS, etc.) | Real-time | ISO 20022 / proprietary | N/A (regulatory infrastructure) | H
Product Factory | SSB Review Gateway | Workflow | Product definitions for Fatwa review | Per new product / change | Workflow engine | Core Shariah governance | H
All Modules | Workflow Engine | Event-driven | Workflow triggers, state transitions | Real-time | BPMN engine API | SSB checkpoints embedded in workflows | H
All Modules | Notification Engine | Event-driven | Notification triggers, templates, recipients | Real-time | Event bus | Arabic notification content | M
Digital Channels | CIF + All Products | Request-Response | Customer data, account data, transaction initiation | Real-time | REST API | Islamic product presentation | H
Digital Channels | National ID (Absher/UAE Pass) | Federation | Authentication tokens, identity verification | Per login / onboarding | SAML / OIDC | N/A (authentication) | H
Regulatory Reporting | GL + All Modules | Batch | Aggregated financial and prudential data | Periodic (daily/monthly/quarterly) | ETL / Internal API | Islamic-specific regulatory schedules | H
Shariah Compliance Engine | All Transactional Modules | Real-time + Batch | Transaction screening results, compliance flags | Real-time screening + periodic audit sampling | Internal API + Batch | Core Shariah compliance function | H
Zakat Module | GL + Asset Modules | Batch | Asset values, liability values for Zakat base | Annual | Internal API | Zakat computation methodology | H
Treasury | GL + Liquidity | Event-driven | Deal postings, position updates | Real-time | Internal API | Islamic instrument classification | H
Trade Finance | Payment Hub + SWIFT | Workflow | LC advices, payment instructions, document notifications | Per transaction | SWIFT MT/MX + Internal API | Murabaha LC ownership sequence | H
Credit Bureau | CIF + Financing | Request-Response | Credit inquiry, report retrieval | Per application | Web service (SIMAH/AECB API) | Used within Islamic credit decisioning | H
Data Warehouse | All Modules | Batch ETL | Full transactional and master data extract | Daily/Nightly | ETL pipeline | Islamic contract attributes preserved | M
ZATCA (KSA) | Zakat + GL | API | Zakat return filing, VAT returns | Periodic | ZATCA API | Mandatory in KSA | H